## 2018 BUDGET
MDS Corporate Operating Expenses
Jan. 1, 2018 through Dec. 31, 2018
Month
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Officers | [13 empty] | 0
Managing Director | [13 empty] | 0
Pilot | [13 empty] | 0
Directors | [13 empty] | 0
Office Manager | 1739 | 1739 | 1739 | 1739 | 1739 | 1739 | 1739 | 1739 | 1739 | 1739 | 1739 | 1739 |  | 20868
Office Assistant | [5 empty] | 978 | 978 | 978 | 978 | 978 | 978 | 978 |  | 6846
2 A&P Mechanics | 3533 | 3533 | 3533 | 3533 | 3533 | 3533 | 3533 | 3533 | 3533 | 3533 | 3533 | 3533 |  | 42396
A&P Assistant | 1304 | 1304 | 1304 | 1304 | [9 empty] | 5216
Computer Equipment | [13 empty] | 0
Office Supplies | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 |  | 1800
Miscellaneous Supplies | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 |  | 360
Fuel & Oil |  |  |  | 4000 | [6 empty] | 4000 |  |  | 8000
Office Rent | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 |  | 7800
Utilities | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 |  | 2160
Phone & Internet | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 |  | 4800
Travel Expenses | 1200 |  |  |  | 5000 | [8 empty] | 6200
Attorneys |  | 2000 | [7 empty] | 2000 |  |  |  | 4000
Accountants |  | 1500 | [8 empty] | 1500 |  |  | 3000
Auditors | 1800 | [12 empty] | 1800
D&O Insurance | 800 | [12 empty] | 800
Aircraft Insurance |  |  | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 |  | 4000
Health Insurance | [13 empty] | 0
Media & Promotions |  |  |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 15000
Web Site |  |  | 500 |  |  |  |  | 500 | [5 empty] | 1000
Loans | [13 empty] | 0
Bank Charges | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 |  | 600
Aircraft Restoration | 22000 | 11000 | 11000 |  | 175000 | 20000 | 6000 | 14000 | 2000 | 0 | 0 |  |  | 261000
Office Furnishings | [13 empty] | 0
Office Maintenance | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 |  | 900
0
0
0
0
0
0
| 33911 | 22611 | 20011 | 12511 | 192207 | 28185 | 14185 | 27685 | 10185 | 10185 | 18685 | 8185 |  | 398546
Revenue | Month
Revenue Source | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Donations/ Individuals | 25000 | 20000 | 18000 | 15000 | 15000 | 25000 | 2000 | 10000 | 15000 | 12000 | 20000 | 20000 |  | 197000
Corporate Sponsors | 0 | 0 | 0 | 2000 | 175000 | 2000 | 10000 | 5000 | 5000 | 2000 | 0 | 2000 |  | 203000
Grants | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Skydiving Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Air Shows | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
T-Shirt Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 25000 | 20000 | 18000 | 17000 | 190000 | 27000 | 12000 | 15000 | 20000 | 14000 | 20000 | 22000 |  | 400000

## 2019 BUDGET
MDS Corporate Operating Expenses
Jan. 1, 2019 through Dec. 31, 2019
Month
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Officers | [13 empty] | 0
Managing Director | [13 empty] | 0
Pilot | [13 empty] | 0
Directors | [13 empty] | 0
Office Manager | 2718 | 2718 | 2718 | 2718 | 2718 | 2718 | 2718 | 2718 | 2718 | 2718 | 2718 | 2718 |  | 32616
Office Assistant | [5 empty] | 978 | 978 | 978 | 978 | 978 | 978 | 978 |  | 6846
2 A&P Mechanics | 4022 | 4022 | 4022 | 4022 | 4022 | 4022 | 4022 | 4022 | 4022 | 4022 | 4022 | 4022 |  | 48264
A&P Assistant | 1739 | 1739 | 1739 | 1739 | 1739 | 1739 | 1739 | 1739 | 1739 | 1739 | 1739 | 1739 |  | 20868
Computer Equipment | [13 empty] | 0
Office Supplies | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 |  | 1800
Miscellaneous Supplies | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 |  | 360
Fuel & Oil |  |  |  | 4000 | [6 empty] | 4000 |  |  | 8000
Office Rent | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 |  | 7800
Utilities | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 |  | 2160
Phone & Internet | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 |  | 4800
Travel Expenses | 5000 | [7 empty] | 5000 |  |  |  |  | 10000
Attorneys |  | 2000 | [7 empty] | 2000 |  |  |  | 4000
Accountants |  | 1500 | [8 empty] | 1500 |  |  | 3000
Auditors | 1800 | [12 empty] | 1800
D&O Insurance | 800 | [12 empty] | 800
Aircraft Insurance | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 |  | 4800
Health Insurance | [13 empty] | 0
Media & Promotions | 5000 |  |  | 5000 |  |  |  | 5000 |  |  | 5000 |  |  | 20000
Web Site |  | 500 | [5 empty] | 500 | [5 empty] | 1000
Loans | [13 empty] | 0
Bank Charges | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 |  | 600
Aircraft Restoration | 5000 | 2000 | 20000 |  | 20000 |  | 24000 | 0 | 15000 | 30000 | 48000 | 4000 |  | 168000
Office Furnishings | [13 empty] | 0
Office Maintenance | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 |  | 900
0
0
0
0
0
0
| 25392 | 14892 | 43196 | 25596 | 16196 | 21196 | 23696 | 17796 | 41196 | 25696 | 16196 | 19466 |  | 348414
Revenue | Month
Revenue Source | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Donations/ Individuals | 20000 | 2000 | 25000 | 25000 | 25000 | 10000 | 35000 | 15000 | 25000 | 2000 | 10000 | 20000 |  | 214000
Corporate Sponsors | 5000 | 20000 | 2000 | 5000 | 10000 | 2000 | 2000 | 5000 | 5000 | 40000 | 45000 | 10000 |  | 151000
Grants | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Skydiving Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Air Shows | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
T-Shirt Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 50600 | 6000 | 3000 | 70600 | 6000 | 6000 | 53600 | 0 | 0 | 45600 |  | 365000

## 2020 BUDGET
MDS Corporate Operating Expenses
Jan. 1, 2020 through Dec. 31, 2020
Month
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Officers | [13 empty] | 0
Managing Director | 2174 | 2174 | 2174 | 2174 | 2174 | 2174 | 2174 | 2174 | 2174 | 2174 | 2174 | 2174 |  | 26088
Pilot |  |  | 1304 | 1304 | 1304 | 1304 | 1304 | 1304 | 1304 | 1304 | 1304 | 1304 |  | 13040
Directors | [13 empty] | 0
Office Manager | 2718 | 2718 | 2718 | 2718 | 2718 | 2718 | 2718 | 2718 | 2718 | 2718 | 2718 | 2718 |  | 32616
Office Assistant | 1304 | 1304 | 1304 | 1304 | 1304 | 1304 | 1304 | 1304 | 1304 | 1304 | 1304 | 1304 |  | 15648
A&P Mechanics | 3533 | 3533 | 3533 | 3533 | 3533 | 3533 | 3533 | 3533 | 3533 | 3533 | 3533 | 3533 |  | 42396
A&P Assistant | 2174 | 2174 | 2174 | 2174 | 2174 | 2174 | 2174 | 2174 | 2174 | 2174 | 2174 | 2174 |  | 26088
Computer Equipment |  |  |  | 900 |  |  |  | 600 | [5 empty] | 1500
Office Supplies | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 |  | 1800
Miscellaneous Supplies | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 |  | 360
Fuel & Oil |  |  | 5000 |  |  | 5000 |  |  | 5000 |  |  | 5000 |  | 20000
Office Rent | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 | 650 |  |  | 7150
Utilities | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 |  |  | 1980
Phone & Internet | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 |  |  | 4400
Travel Expenses |  | 2500 |  |  | 2500 |  |  | 2500 |  |  | 2500 |  |  | 10000
Attorneys |  |  | 2000 | [6 empty] | 2000 |  |  |  | 4000
Accountants | 500 |  | 500 |  |  | 500 |  |  | 500 |  |  |  |  | 2000
Auditors | 2500 | [12 empty] | 2500
D&O Insurance | [13 empty] | 0
Aircraft Insurance |  |  | 2000 |  |  | 2000 |  |  | 2000 |  |  | 2000 |  | 8000
Health Insurance | [13 empty] | 0
Media & Promotions | 10000 |  |  | 10000 |  |  | 10000 |  |  | 10000 |  |  |  | 40000
Web Site | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 1200
Loans | [13 empty] | 0
Bank Charges | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 |  | 900
Aircraft Restoration |  |  | 10000 | [5 empty] | 10000 |  |  |  |  | 20000
Office Furnishings |  |  |  | 1000 |  |  |  | 1000 | [5 empty] | 2000
Office Maintenance | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 1200
0
0
0
0
0
0
| 26588 | 16088 | 34392 | 26792 | 17392 | 22392 | 24892 | 18992 | 32392 | 26892 | 17392 | 20662 |  | 284866
Revenue | Month
Revenue Source | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Donations/ Individuals | 20000 | 0 | 45000 | 0 | 0 | 60000 | 5000 | 5000 | 40000 | 0 | 0 | 40000 |  | 215000
Corporate Sponsors | 0 | 0 | 10000 | 0 | 0 | 10000 | 0 | 0 | 10000 | 0 | 0 | 10000 |  | 40000
Grants | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Skydiving Operations | 0 | 0 | 0 | 6000 | 3000 | 3000 | 4000 | 4000 | 6000 | 0 | 0 | 0 |  | 26000
Air Shows | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 |  | 8000
T-Shirt Sales | 0 | 0 | 600 | 0 | 0 | 600 | 0 | 0 | 600 | 0 | 0 | 600 |  | 2400
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 20000 | 0 | 55600 | 6000 | 3000 | 75600 | 11000 | 11000 | 58600 | 0 | 0 | 50600 |  | 291400

## REVENUE ESTIMATES
Revenue | Month | [11 empty] | 2018
Revenue Source | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Donations/ Individuals | 25000 | 20000 | 18000 | 15000 | 15000 | 25000 | 2000 | 10000 | 15000 | 12000 | 20000 | 20000 |  | 197000
Corporate Sponsors | 0 | 0 | 0 | 2000 | 175000 | 2000 | 10000 | 5000 | 5000 | 2000 | 0 | 2000 |  | 203000
Grants | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Skydiving Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Air Shows | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
T-Shirt Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 25000 | 20000 | 18000 | 17000 | 190000 | 27000 | 12000 | 15000 | 20000 | 14000 | 20000 | 22000 |  | 400000
Revenue | Month | [11 empty] | 2019
Revenue Source | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Donations/ Individuals | 20000 | 2000 | 25000 | 25000 | 25000 | 10000 | 35000 | 15000 | 25000 | 2000 | 10000 | 20000 |  | 214000
Corporate Sponsors | 5000 | 20000 | 2000 | 5000 | 10000 | 2000 | 2000 | 5000 | 5000 | 40000 | 45000 | 10000 |  | 151000
Grants | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Skydiving Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Air Shows | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
T-Shirt Sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 50600 | 6000 | 3000 | 70600 | 6000 | 6000 | 53600 | 0 | 0 | 45600 |  | 365000
Revenue | Month | [11 empty] | 2020
Revenue Source | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Donations/ Individuals | 20000 | 0 | 45000 | 0 | 0 | 60000 | 5000 | 5000 | 40000 | 0 | 0 | 40000 |  | 215000
Corporate Sponsors | 0 | 0 | 10000 | 0 | 0 | 10000 | 0 | 0 | 10000 | 0 | 0 | 10000 |  | 40000
Grants | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Skydiving Operations | 0 | 0 | 0 | 6000 | 3000 | 3000 | 4000 | 4000 | 6000 | 0 | 0 | 0 |  | 26000
Air Shows | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 |  | 8000
T-Shirt Sales | 0 | 0 | 600 | 0 | 0 | 600 | 0 | 0 | 600 | 0 | 0 | 600 |  | 2400
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 20000 | 0 | 55600 | 6000 | 3000 | 75600 | 11000 | 11000 | 58600 | 0 | 0 | 50600 |  | 291400
REVENUE
[12 empty] | 2018 |  | 400000
[12 empty] | 2019 |  | 365000
[12 empty] | 2020 |  | 291400
[12 empty] | TOTAL |  | 1056400

## RESTORATION ESTIMATES
24 Month Restoration
MDS Project Budget Summary
Michael Rouse - Jan.- 2018
Task | Aircraft Item | Start | End | Duration |  | Cost | Total Cost
|  | (Month) |  |  | Quantity
A. Engines |  | 8 | 10 | 2
2 Pratt Whitney 1830 / 94 |  |  |  |  | 2 | 75000 | 150000 | 150000
A.1. | Engine Accessories | 11 | 14 | 3
| Starter |  |  |  | 2 | 900 | 1800
| Hydraulic Pump |  |  |  | 2 | 750 | 1500
| Tachometer |  |  |  | 2 | 550 | 1100
| Prop Governor |  |  |  | 2 | 650 | 1300
| Generator |  |  |  | 2 | 1100 | 2200
| Carburetor |  |  |  | 2 | 2700 | 5400
| Fuel Pump |  |  |  | 4 | 900 | 3600
| Magneto Blocks |  |  |  | included in overhaul
| SFLNH Magnetos |  |  |  | included in overhaul
| Ignition Wires |  |  |  | included in overhaul
| Engine Mounts & X-rays |  |  |  | 2 | 1000 | 2000
| Fuel lines |  |  |  | 2 | 400 | 400
| Electric Fuel Pump Motor |  |  |  | included in overhaul
| Oil Lines |  |  |  | 2 | 400 | 400
| Oil Cooler |  |  |  | 2 | 2500 | 5000 | 24700
B1. | Propellers | 9 | 10 | 1
| Hubs & Blades |  |  |  | 2 | 7000 | 14000 | 14000
C1. | Engine Controls | 12 | 13 | 1
| Throttle |  |  |  | ok |  | 0
| Propeller |  |  |  | ok |  | 0
| Mixture |  |  |  | ok |  | 0
| Carburetor Heat |  |  |  | ok |  | 0
D1. | Flight Control Cables | 7 | 8 | 1 |  |  |  | Inspect, Clean & Lube
| Rudder |  |  |  | ok | 0 | 0
| Elevator |  |  |  | ok | 0 | 0
| Aileron |  |  |  | ok | 0 | 0
| Trim |  |  |  | 1 | 1500 | 1500 | 1500
E1. | Landing Gear | 7 | 8 | 1
| Main Tires |  |  |  | 2 | 2100 | 4200
| Main Tubes |  |  |  | 2 | 400 | 800
| Tail Wheel Tire |  |  |  | 1 | 500 | 500
| Tail Wheel Tube |  |  |  | 1 | 200 | 200
| Brake Drums Used Overhauled |  |  |  | 4 | 1300 | 5400
| Brake Drum Expander Tubes |  |  |  | 4 | 2500 | 10000
| Brake Pucks |  |  |  | 56 | 75 | 4200
| Brake Actuator |  |  |  |  | 0 | 0
| Hydraulic Accumulator Pump |  |  |  |  | 0 | 0
| rebush landing gear |  |  |  | 2 | 400 | 800 | 20000
F1. | Metal Airframe
A. | Cockpit Exterior | 14 | 16 | 2
| Sliding Side Windows & Frames |  |  |  | 2 | 250 | 500
| Weather Proof Nose |  |  |  | 1 | 200 | 200
| Escape Hatch Seal |  |  |  | 1 | 100 | 100
| Windshield |  |  |  | 2 | 300 | 600 | 1400
B. | Fuselage Exterior | 16 | 18 | 2
| T88 Batteries | 10 |  |  | 2 | 1000 | 2000
| Main Cabin Windows |  |  |  | 8 | 1500 | 1500
| Door Seals |  |  |  | 1 | 100 | 100
| Fuel Drains |  |  |  | 6 | 75 | 450
| Fuel Cap Seals |  |  |  | 4 | 50 | 200
| Landing Lights |  |  |  | 2 | 200 | 400
| Position lights & beacon |  |  |  | 2 | 700 | 1400
| Static Wicks |  |  |  | 10 | 30 | 300 | 6350
C. | Aircraft Paint | 23 | 24 | 1
| Three Color Strip & Paint |  |  |  | 1 | 48000 | 48000 | 48000
G1. | Fabric Control Surfaces | 3 | 8 | 5
| R/L Ailerons |  |  |  | 2 | 6000 | 12000
| R/L Elevator |  |  |  | 2 | 10000 | 20000
| Rudder | 7 | 8 | 1 | 1 | 12000 | 12000 | 44000
H1. | Interior Cabin | 21 | 22 | 1
| Jump Lights |  |  |  | 1 | 600 | 600
| Jump Door |  |  |  | 1 | 600 | 800
| Jump bench's |  |  |  | ok | 0 | 0
| Stereo |  |  |  | 1 | 1200 | 1100
| Carpet FAA Approved |  |  |  | 1 | 1200 | 1200 | 3700
I1. | Cockpit | 19 | 21 | 2
| Pilot Seats |  |  |  | 2 | 300 | 600
| Head Liner |  |  |  | 1 | 8000 | 8000
| Cabinet |  |  |  | 1 | 300 | 300
| Passenger Seats |  |  |  | ?
| Bulk Head |  |  |  | 1 | 400 | 400 | 9300
J1. | Documents | 21
| SIP Inspection Doc. |  |  |  | 1 | 5000 | 5000 | 5000
K1. | Instrumentation & Avionics | 21 | 22 | 1
| Update Instrument Panel |  |  |  | 1 | 30000 | 30000 | 30000
L1. | Labor
| On Staff Mechanics for 18 Months |  |  |  | 2 | 42000 | 84000
One to be an FAA rated IA
M1. | Ferry, Shipping & Transportation |  |  |  | 1 | 20000 | 20000 | 20000
N1. | Miscellaneous Expense |  |  |  | 1 | 20000 | 20000 | 20000
|  |  | Total Cost |  |  |  | 488050 | 397950
Total without Labor

## EMPLOYEE REPORT
FY 2018
Employee Designation | Number | Position | Monthly Salary | Social Security Company | Medicare Company | Federal Unemployment | State Unemployment | Total Monthly Salary | Total Quarterly Salary
1 |  | Managing Director |  | 0 | 0 | 0 | 0 | 0 | 0
2 | 1 | Office Manager | 1600 | 99.2 | 23.0368 | 12.064 | 4.936 | 1739.2368 | 5217.7104
3 | 2 | A&P Mechanic | 3250 | 201.5 | 46.7935 | 24.505 | 10.0263 | 7065.6495 | 21196.9485
4 |  | IA Mechanic | 1200 | 74.4 | 17.2776 | 9.048 | 3.702 | 1304.4276 | 7826.5656
5 | 1 | Office Assistant | 900 | 55.8 | 12.9582 | 6.786 | 2.7765 | 978.3207 | 2934.9621
6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 11087.6346 | 37176.1866
FY 2019
Employee Designation | Name | Position | Monthly Salary | Social Security Company | Medicare Company | Federal Unemployment | State Unemployment | Total Monthly Salary | Total Quarterly Salary
1 |  | Office Assistant | 900 | 55.8 | 12.9582 | 6.786 | 2.7765 | 978.3207 | 2934.9621
2 |  | Office Manager | 2500 | 155 | 35.995 | 18.85 | 7.7125 | 2717.5575 | 8152.6725
3 |  | Managing Director |  | 0 | 0 | 0 | 0 | 0 | 0
4 |  | A&P Mechanic | 3700 | 229.4 | 53.2726 | 27.898 | 11.4145 | 4021.9851 | 12065.9553
5 |  | IA Mechanic | 1600 | 99.2 | 23.0368 | 12.064 | 4.936 | 1739.2368 | 5217.7104
6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 9457.1001 | 28371.3003
FY 2020
Employee Designation | Name | Position | Monthly Salary | Social Security Company | Medicare Company | Federal Unemployment | State Unemployment | Total Monthly Salary | Total Quarterly Salary
1 |  | Office Assistant | 1200 | 74.4 | 17.2776 | 9.048 | 3.702 | 1304.4276 | 3913.2828
2 |  | Office Manager | 2500 | 155 | 35.995 | 18.85 | 7.7125 | 2717.5575 | 8152.6725
3 |  | Managing Director | 2000 | 124 | 28.796 | 15.08 | 6.17 | 2174.046 | 6522.138
4 |  | A&P Mechanic | 3250 | 201.5 | 46.7935 | 24.505 | 10.0263 | 3532.8247 | 10598.4742
5 |  | A&P Assistant | 2000 | 124 | 28.796 | 15.08 | 6.17 | 2174.046 | 6522.138
6 |  | Pilot | 1200 | 74.4 | 17.2776 | 9.048 | 3.702 | 1304.4276 | 3913.2828
[8 empty] | 13207.3295 | 39621.9883